## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
February 3, 2022

## Slide 2: RHO Program Implementation Timeline
Feb - Mar 2021
Baseline data collection begins
Mar - May 2021
Initiate site training
Initiate monthly phone calls
May - Aug 2021
Jun 2021 - Feb 2022
Feb - Aug 2022
Aug 2022 - Feb 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
Feb - Aug 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 3
Chart: Site Start Up Progress
| Vanderbilt | Maryland | Kentucky | San Diego | Peyton Manning | Nationwide | Colorado | MGH | New York | Dartmouth | Cincinnati | CHOP | BCH | Arkansas
Executed Contract | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
IRB Approval | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Equipment Available | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
 | - Enrolling
 | - Activated but not enrolling
 | - Patient identified, not yet enrolled

## Slide 4: RHO Implementation Trial Consort Diagram
Average HOT Duration: 56±34

## Slide 5
Goal
Chart: Recorded Home Oximetry Program Implementation Trial Enrollment (July 2021 to Present)
| Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22
Participants Enrolled | 3 | 3 | 1 | 3 | 7 | 1 | 5
UCL | 8.7237 | 8.7237 | 8.7237 | 8.7237 | 8.7237 | 8.7237 | 8.7237
+2 Sigma | 6.911 | 6.911 | 6.911 | 6.911 | 6.911
+1 Sigma | 5.0984 | 5.0984 | 5.0984 | 5.0984 | 5.0984
Average | 3.2857 | 3.2857 | 3.2857 | 3.2857 | 3.2857 | 3.2857 | 3.2857
-1 Sigma | 1.4731 | 1.4731 | 1.4731 | 1.4731 | 1.4731
-2 Sigma | 0 | 0 | 0 | 0 | 0
LCL | 0 | 0 | 0 | 0 | 0
Projected Enrollment | 3.8 | 4.3 | 4.3 | 14.9 | 14.9 | 14.9 | 14.9

## Slide 6: Projected vs. Actual Enrollment Into the RHO Program
Site Name | Estimate per Year | Estimate per Month | Current per Month | Eligible to Date | Followed to Date N(%)
WAVE 1 |  |  |  |  | 
Boston Children's Hospital | 40 | 3.3 | 0.7 | 6 | 5 (83)
Dartmouth-Hitchcock | 20 | 1.7 | 0.0 | 0 | 0
Maria Fareri Children's | 14 | 1.2 | 0.8 | 2 | 2 (100)
Massachusetts General Hospital | 13 | 1.1 | 0.4 | 3 | 3 (100)
University of Maryland | 20 | 1.7 | 1.3 | 8 | 7 (88)
WAVE 2 |  |  |  |  | 
Arkansas Children's Hospital | 48 | 4.0 | 1.1 | 3 | 3 (100)
Children's Hospital of Phil. | 50 | 4.2 | 0.0 | 5 | 0
Cincinnati Children's Hospital | 50 | 4.2 | 0.0 | 0 | 0
National Jewish Health | 250 | 20.8 | 0.0 | 0 | 0
Nationwide Children's Hospital | Not Provided | Not Provided | 0.0 | 0 | 0
Peyton Manning Children's Hospital | 25 | 2.1 | 0.0 | 0 | 0
U. of California, San Diego | 65 | 5.4 | 1.1 | 4 | 3 (75)
U. of Kentucky Children's Hospital | 50 | 4.2 | 0.0 | 0 | 0
*Only showing sites with executed contracts

## Slide 7: Barriers to Enrollment
Screening Logs:
  Please ensure your site is screening ALL potentially eligible infants discharged home on respiratory support despite their participation status in the RHO program
  Completion of the screening form in REDCap is essential in the accuracy of the overall denominator and ensuring all eligible infants are captured across all sites
  Proper completion of the screening form would further aid in providing an accurate reach of the RHO program- a primary outcome of the implementation trial

## Slide 8: REDCap User Access Groups
10/14 sites have access to their Data Access Group (DAG)
7/7 enrolling sites have access to their DAG
6/7 enrolling sites filled out demographic forms for their patients

## Slide 9: Implementation Related Problems

## Slide 10
Goal
Chart: Recorded Home Oximetry Implementation Trial Related Barriers and Problems
| 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562
Problem Count | 1 | 6 | 2 | 1 | 5 | 4 | 5
UCL | 8.9835 | 8.9835 | 8.9835 | 8.9835 | 8.9835 | 8.9835 | 8.9835
+2 Sigma | 7.1319 | 7.1319 | 7.1319 | 7.1319 | 7.1319 | 7.1319 | 7.1319
+1 Sigma | 5.2802 | 5.2802 | 5.2802 | 5.2802 | 5.2802 | 5.2802 | 5.2802
Average | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286 | 3.4286
-1 Sigma | 1.5769 | 1.5769 | 1.5769 | 1.5769 | 1.5769 | 1.5769 | 1.5769
-2 Sigma | 0 | 0 | 0 | 0 | 0 | 0 | 0
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 11: RAD 97 Configuration
Please make sure that the light of the wi-fi symbol is green
If it is blue , either:
  the device is not configured to our SafetyNet
  the device is connected to Guest Network
  the Wi-Fi signal is too low
Solution
The providing homecare company should contact their local Masimo account manager for assistance
If the issue persists, let the RHO Leadership know and we will contact Masimo’s leadership

## Slide 12: Troubleshooting Guides
Were disseminated to sites last week
Home care companies to receive their own version based on their role

## Slide 13: Oxygen Flow Rate Variations Between Sites
Need to decide on the protocol for infants on <125 cc/min flow rate close to discharge:
  a) Cannot participate
  b) Increase the flow rate to 125 cc/min at discharge
  c) Accommodate <125 cc/min flow rate in the protocol
Poll Results: Total of 9/14 Responses
  Option A: 2 (22%)
  Option B: 3 (33%)
  Option C: 1 (11%)
  Option A +B: 1 (11%)
  Option B+ C: 2 (22%)
The RHO program at UMass has been operating within set oxygen flow rate parameters

## Slide 14: Responses to Bi-Weekly emails
If you are following the algorithm’s determination, you only need to respond with one letter.
A – Weaned
B – Maintained
C – Increased
If you are not following the algorithm’s determination, please type the appropriate letter and a reason for not following the algorithm’s determination.
To ensure proper documentation of the data, please be sure to respond to the bi-weekly emails. If we don’t receive a response, we will ask for clarification on the subsequent email
Email from UMass:
Response from a Site:

## Slide 15: Deviation Types
Chart: 
| Technological barrier with SafetyNet connection (no data captured) | Wi-Fi connectivity issues (no data captured) | Patient not connected to oximeter (no data captured) | Damaged equipment: probes, cord etc. (no data captured) | Wrong device provided (no data captured) | Currently Admitted (no data captured) | No data captured, reason unknown | Provider did not follow guideline suggestion | Did not meet minimum time but change in flow rate occurred anyway | Data was not analyzed at set time | Parent felt uncomfortable changing flow rate | Parent titrated flow rates
 | 41 | 5 | 12 | 12 | 6 | 2 | 26 | 31 | 1 | 0 | 9 | 6
Total Reports | Reports with Deviation(s)
432 | 139 (32%)
No Data Captured

## Slide 16
Chart: Percent Compliance with the Recorded Home Oximetry Algorithm Across All Implementation Sites
| Jul. 2021 (n=15) | Aug. 2021 (n=51) | Sept. 2021 (n=65) | Oct. 2021 (n=63) | Nov. 2021 (n=75) | Dec. 2021 (n=91) | Jan. 2022 (n=75)
Percent Compliance | 0.66667 | 0.94118 | 0.92308 | 0.9 | 0.91 | 0.97802 | 0.96
UCL | 1.0795 | 1.0795 | 1.0795 | 1.0795 | 1.0795 | 1.0795 | 1.0795
+2 Sigma | 1.0187 | 1.0187 | 1.0187 | 1.0187 | 1.0187 | 1.0187 | 1.0187
+1 Sigma | 0.95784 | 0.95784 | 0.95784 | 0.95784 | 0.95784 | 0.95784 | 0.95784
Average | 0.89699 | 0.89699 | 0.89699 | 0.89699 | 0.89699 | 0.89699 | 0.89699
-1 Sigma | 0.83615 | 0.83615 | 0.83615 | 0.83615 | 0.83615 | 0.83615 | 0.83615
-2 Sigma | 0.7753 | 0.7753 | 0.7753 | 0.7753 | 0.7753 | 0.7753 | 0.7753
LCL | 0.71446 | 0.71446 | 0.71446 | 0.71446 | 0.71446 | 0.71446 | 0.71446

## Slide 17: Parent Advisory Board Meeting
Bi-annual Parent Advisory Board meeting will be held on
Agenda Items:
    RHO Implementation progress
    Family Expectations of Weaning
    Family Communication
    Disseminating the RHO Program
PAB Suggestions
  Informational Brochure (including data and numbers)
  Invitation to Virtual Music Classes
  Facebook support group
  *Please be sure to notify Heather of families who would be interested in joining

## Slide 18: Invoicing
Our grants office will be reaching out to all sites for invoices
Please notify Heather who the primary delegate at your site

## Slide 19: RHO Pre- Implementation Provider Survey
Please be sure to enter a 4-digit identification number to allow us to link your responses to this survey with future surveys
  4-digit ID should be something you could easily remember, as it will be used again for future surveys (preferably last four digits of your cell phone)
Please disseminate the REDCap link to ALL study staff at your site who are involved in the RHO program
REDCap Link: https://arcsapps.umassmed.edu/redcap/surveys/?s=AA4XKYM7KH

## Slide 20: RHO Program Website
All resources, including training documents, the RHO manual, and other templates can be found on the RHO website at www.umassmed.edu/rho-program
Navigate to “Member Login” and log in with the following credentials to access the documents
  Username: RHO
  Password: Oximetry14

## Slide 21: Closing Thoughts
Questions or Comments?