1/7/20 RHO Implementation Investigator Meeting Minutes

| Site | Attendance |
| --- | --- |
| Arkansas Children's Hospital |  |
| Boston Children's Hospital |  |
| Children's Hospital of Phil. |  |
| Cincinnati Children's Hosp |  |
| Colorado |  |
| Dartmouth |  |
| Maria Fareri Children's |  |
| Mass General |  |
| Nationwide Children's |  |
| St. Vincent Neighborhood Hosp, Indianapolis |  |
| U. of California, San Diego |  |
| U. of Kentucky Children's Hosp |  |
| University of Maryland |  |
| Vanderbilt |  |

Site Selection for Implementation Waves

- Restricting Wave 1 to the northeast due to COVID-19 travel restrictions

Baseline Data Collection

- Majority of baseline data will be obtained from VON

- HOT duration and number of adverse events will also be collected

- Goal is to be easy for sites

  - If this data collection is not part of standard practice, will need to implement questions into outpatient visits

Homecare Companies

- Important to contact your site’s care coordinators that will be involved in setting up home oxygen supply

- Ask local homecare companies if they can provide WIFI enabled oximeters if they already have them in stock

- Only responsibility of DME company is to provide the equipment and troubleshoot if there are any issues with the monitor

  - UMass (and Dartmouth in wave 2) will be downloading, analyzing, and sharing results with sites twice per week