April 7, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Crystal Vasquez, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- Only 4 more sites to be activated, awaiting IRB approval

Enrollment

- A total of 37 babies followed to date, 13 have weaned with an average HOT duration of 62 days

- Primary reason for exclusion from program = RAD 97 unavailable

  - Working with Masimo to supply more homecare companies with RAD 97’s

- Important part of project - be able to see if can determine infant HOT duration based on initial flow rate

- Should be enrolling about 15 babies per month

Projected vs Actual N of Infants Being Followed

- Seen a dip in enrollment across all active site’s, discussions around potential factors for this

- Have discussed potential factors contributing to low enrollment numbers

- Cincinnati

  - Early 2021 - would not have met estimated number of infants – now back to pre-pandemic estimated number of infants being discharged

- SD

  - Shift in patient demographics with less extremely preterm infants

Barriers to Enrollment

- Please continue to screen all potentially eligible babies being discharged on supplemental oxygen therapy

- Monthly site report’s rely on demographic forms being complete

Upcoming IRB Submission

- Original project plan included adding parental/family survey’s once in the intensive implementation phase

- Working with our Parent Advisory Board to complete survey’s

- Will send all appropriate documents to all sites once receive IRB approval

Reoccurring RAD 97’s Issues and Barriers

- Damaged equipment

  - RHO Team currently tracking and providing feedback to Masimo. Will start to ask for you to provide more info when monitor’s break and need to be switched out

  - Serial numbers are also being provided so that Masimo can help identify the common problems/source of problem

- Probes

  - Has become more of an issue as of late with parents running out of probes more quickly

  - Parent Advisory Board helping to create a fact sheet to preserve probes

- Contacting families

  - Site’s have been having more difficulty contacting parents

Homecare Readiness

- For new sites coming on board or for the first referral to a particular home care try to provide 2-weeks’ notice so that they can refamiliarize themselves with the program and equipment

Parent Advisory Board

- Twice vs. once weekly downloading - strong preference for twice a week check-in especially in first month. Families thought this gave them more reassurance, peace of mind, and someone to direct questions to on a regular basis

  - Once more babies have weaned and we can appropriately categorize duration trajectories we can possibly update algorithm and downloading frequency

  - San Diego, it can be frustrating when an infant is having equipment issues or not receiving data to check in twice per week. The twice per week check-in’s do allow for us to troubleshoot sooner.

  - BCH, uses the EMR portal to communicate with families instead of phone calls. Families have been receptive and team has found it to be effective in communicating maintains.

- Welcomed 2 new families to our PAB who have participated in RHO

  - Goal is to have representation from each hospital, try to identify potential families and let Heather know of anyone who may be interested or looking for more information

- Parents suggested creating a mixed media toolkit for parents - fact sheet, troubleshooting guides etc.

  - In coming months, resources and a parent information page will be added to the website

Invoicing

- Reminder to submit invoice to the UMMS grant’s office

Closing Thoughts

- For children that are more fragile or going home on higher flow rates with there be a change in management or need for further work-up, with more infants and more insight into the need for longer durations of oxygen we can effectively answer this question

- Can we look at artifact and the impact on duration of HOT – with more infants and understanding how the data correlates to the clinical picture we can adequately answer how artifact impacts the recommendations. Although, artifact does get kicked out when analyzing data.

Next Investigator Meeting will be on May 5th at 4pm EST

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count

Site Start-Up Progress

| Wave | Site # | Site Name | Contract Executed |  | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | REDCap Access |  | Site Training Comple | First Enrollment Date | Download Schedule |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave 1 | 102 | Boston Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 106 | Dartmouth-Hitchcock |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | T/F |
|  | 107 | Maria Fareri Children's |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 11/19/2021 | M/Th |
|  | 108 | Massachusetts General Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 7/8/2021 | M/Th |
|  | 113 | University of Maryland |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/23/2021 | M/Th |
|  | 114 | Vanderbilt |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | T/F |
| Wave 2 | 101 | Arkansas Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 103 | Children's Hospital of Phil. |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  |  | TBD |
|  | 104 | Cincinnati Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 105 | National Jewish Health |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 109 | Nationwide Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 3/7/2022 | TBD |
|  | 110 | Peyton Manning Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | TBD |
|  | 111 | U. of California, San Diego |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 11/12/2021 | M/Th |
|  | 112 | U. of Kentucky Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  |  | M/Th |