November 4, 2021

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Maria Matoshi, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

RHO Program Timeline

- Now that every site has completed their trainings and only a few sites are finalizing their contracts we are combining Wave 1 and Wave 2 timelines in our presentations moving forward.

- UMass IRB transferred to a new system. Hopefully, the remaining IRB approvals will be finalized the week of November 15th.

- Pre-determined goal to reach 33% of all eligible infants by February 2022

CITI Certificates

- There are still some sites that haven’t sent all their staffs CITI certificates. Maria sent each site an individualized email with more details.

  - Please reach out to her if you have any questions about CITI certification completion.

Enrollment

- At UMass we have seen changes in baseline rates in VLBW requiring HOT. Have estimates initially provided from each site changed? What are the potential causes?

  - San Diego, Dr. Julie Ryu shared that delays in IRB and home cares having the proper equipment have delayed participation. She also noticed that babies are being born later which decreased the requirement of supplemental O2 at discharge. Additionally, they have a lot of infants with congenital anomalies that don’t qualify for the program.

- Boston Children’s Hospital, Dr. Catherine Sheils mentioned that original estimates included one of their referring NICUs, however, they are not yet participating in the RHO program

- New York, Dr. Sankaran Krishnan shared that due to the pandemic parents are willing to stay in the NICU longer and wean off O2 while inpatient. He is hoping to send a baby home next week.

- CHOP, Dr. Julie Fierro shared that their homecare company of choice experienced shortage of funds due to the Trilogy recall and could not purchase RAD 97s this fiscal year.

- Arkansas Children’s, Dr. Amit Agarwal mentioned that they had around 4 patients who didn’t get included due to delays in their IRB approval. He asked if those infants can be enrolled at their first pulmonary visit within 1 month of their NICU discharge.

  - Once IRB is approved, the effort can be made to enroll them into the program by switching out their device.

  - When RAD 97s are available patients should be discharged home on the device and consent can come later as they will still be followed by the RHO program as SOC.

  - Similar issues have happened at other sites where infants were discharged with the wrong equipment which triggered delays in data transmission.

Referring NICUs

- Suggestion from RHO leadership is to start with one referring NICU to ease into the program and later onboard other hospitals.

  - Some sites have already started conversations with referring NICUs and onboarding to the program.

  - Reach out to Heather if education and training is necessary.

Screening and eligibility

- Please make sure that at least one member of your site’s RHO Implementation team has access to the REDCap so that you can start screening infants going home on respiratory support.

  - Without accurate screening potential reach of implementation cannot be determined.

- Question about missing referrals from referring NICUs

  - VON pull at the beginning and end of the trial will capture any missed infants discharged home on O2.

Baseline Data

- Please send us your baseline data once your site has been IRB approved.

- The instructions on how to obtain baseline data are available on our website.

  - Please reach out to Maria with any questions on baseline data collection and abstraction

Implementation Related Problems

- Heather is working on a site-specific RAD 97 troubleshooting guides (multiple versions for different stakeholders)

Parent Advisory Board Participation

- We would like to have at least one family from each site join our PAB, if you know of potential families that maybe willing to participate please reach out to Heather.

- Our PAB meets every 6-months, our next meeting will take place in February.

Next Investigator Meeting will be on December 2nd at 4pm EST

*Home care companies serving multiple sites, the number of counts is shared between sites.

RAD 97s Count

Site Start-Up Progress

| Wave | Site # | Site Name | Contract Executed |  | cIRB Approval | Local IRB Approval | Regulatory Documents | pSite Communication Plan Agreement | REDCap Access |  | Site Training Comple | Site Implementation Date | First Enrollment Date | Download Schedule |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Wave 1 | 102 | Boston Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 6/1/2021 | 7/8/2021 | M/T |
|  | 106 | Dartmouth-Hitchcock |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 6/1/2021 |  | T/F |
|  | 107 | Maria Fareri Children's |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 6/1/2021 |  | M/T |
|  | 108 | Massachusetts General Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 6/1/2021 | 7/8/2021 | M/T |
|  | 113 | University of Maryland |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 6/1/2021 | 9/9/2021 | M/T |
|  | 114 | Vanderbilt |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 6/1/2021 |  | T/F |
| Wave 2 | 101 | Arkansas Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 103 | Children's Hospital of Phil. |  | ᴏ | N/A | ᴏ | ᴏ | N/A | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 104 | Cincinnati Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 105 | National Jewish Health |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 109 | Nationwide Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 110 | Peyton Manning Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 111 | U. of California, San Diego |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |
|  | 112 | U. of Kentucky Children's Hospital |  | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ | ᴏ |  | 8/1/2021 |  | TBD |