## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
July 7, 2022

## Slide 2: RHO Program Implementation Timeline
Feb - Mar 2021
Baseline data collection begins
Mar - May 2021
Initiate site training
Initiate monthly phone calls
May - Aug 2021
Jun 2021 - Feb 2022
Feb - Aug 2022
Aug 2022 - Feb 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
Feb - Aug 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 3
Chart: Site Start Up Progress
| Vanderbilt | Maryland | Kentucky | San Diego | Peyton Manning | Nationwide | Colorado | MGH | New York | Dartmouth | Cincinnati | CHOP | BCH | Arkansas
Executed Contract | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
IRB Approval | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Equipment Available | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
 | - Enrolling
 | - Activated but not enrolling
 | - Patient identified, not yet enrolled

## Slide 4: RHO Implementation Trial Consort Diagram
Average HOT Duration:
74 ± 55

## Slide 5
Goal
Chart: Recorded Home Oximetry Program Implementation Trial Enrollment (July 2021 to Present)
| Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22 | Jun-22 | Jul-22
Participants Enrolled | 3 | 3 | 1 | 5 | 5 | 1 | 8 | 3 | 8 | 3 | 11 | 6 | 2
UCL | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096 | 11.1 | 11.096 | 11.096
+2 Sigma | 8.9428 | 8.9428 | 8.9428 | 8.9428 | 8.9428 | 8.9428 | 8.9428 | 8.9428
+1 Sigma | 6.7896 | 6.7896 | 6.7896 | 6.7896 | 6.7896 | 6.7896 | 6.7896 | 6.7896
Average | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364 | 4.6364
-1 Sigma | 2.4831 | 2.4831 | 2.4831 | 2.4831 | 2.4831 | 2.4831 | 2.4831 | 2.4831
-2 Sigma | 0.32992 | 0.32992 | 0.32992 | 0.32992 | 0.32992 | 0.32992 | 0.32992 | 0.32992
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projected Enrollment | 3.8 | 4.3 | 4.3 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9

## Slide 6: Enrollment by Site
Site Name | 1st patient enrolled | Site IRB Approved | Duration of Implementation in Months | Eligible | Followed | Withdrawn | Active | Weaned | Avg HOT Duration
WAVE 1 |  |  |  |  |  |  |  |  | 
Boston Children's Hospital | 7/8/2021 | 10/4/2021 | 10.9 | 9 | 8 (89%) | 1 | 2 | 5 | 94 ± 90
Dartmouth-Hitchcock | Jan. 2022 | 10/4/2021 | 8.0 | 11 | 11 (100%) |  | 7 | 4 | 42.3 ± 30.2
Maria Fareri Children's | 11/18/2021 | 7/10/2021 | 6.5 | 2 | 2 (100%) |  | 0 | 2 | 90 ± 52
Massachusetts General Hospital | 7/8/2021 | 10/4/2021 | 10.9 | 6 | 5 (83%) | 1 | 2 | 2 | 90.5 ± 40
University of Maryland | 8/21/2021 | 10/4/2021 | 9.5 | 14 | 11 (79%) | 4 | 1 | 6 | 54 ± 39
Vanderbilt | 4/28/2021 | 7/21/2021 | 10.5 | 7 | 2 (29%) |  | 2 | 0 | 
WAVE 2 |  |  |  |  |  |  |  |  | 
Arkansas Children's Hospital | 10/20/2021 | 1/28/2022 | 7.5 | 4 | 4 (100%) | 1 | 2 | 1 | 90
Children's Hospital of Phil. | 5/26/2022 | 10/20/2021 | 7.5 | 13 | 2 (15%) |  | 2 | 0 | 
Cincinnati Children's Hospital |  | 4/15/2022 |  | 0 |  |  | 0 | 0 | 
National Jewish Health |  | 10/4/2021 | 8.0 | 0 |  |  | 0 | 0 | 
Nationwide Children's Hospital | 3/4/2022 | 10/4/2021 | 8.0 | 17 | 13 (76%) | 4 | 9 | 3 | 56 ± 18
Peyton Manning Children's Hospital |  |  |  | 0 |  |  | 0 | 0 | 
U. of California, San Diego | 11/10/2021 | 10/4/2021 | 6.8 | 7 | 3 (43%) | 1 | 2 | 1 | 28
U. of Kentucky Children's Hospital |  |  |  | 0 |  |  | 0 | 0 | 

## Slide 7: Projected vs. Actual Enrollment Into the RHO Program
Site Name | Site IRB Approved | Estimate per Year | Estimate per Month | Current per Month | Estimated enrollment to Date
WAVE 1 |  |  |  |  | 
Boston Children's Hospital | 10/4/2021 | 40 | 3.3 | 0.7 | 13.3
Dartmouth-Hitchcock | 10/4/2021 | 20 | 1.7 | 1.4 | 1.7
Maria Fareri Children's | 7/10/2021 | 14 | 1.2 | 0.3 | 4.7
Massachusetts General Hospital | 10/4/2021 | 13 | 1.1 | 0.5 | 4.3
University of Maryland | 10/4/2021 | 20 | 1.7 | 0.7 | 5.0
Vanderbilt | 7/21/2021 | 70 | 5.8 | 0.2 | 23.3
WAVE 2 |  |  |  |  | 
Arkansas Children's Hospital | 1/28/2022 | 48 | 4.0 | 0.4 | 
Children's Hospital of Phil. | 10/20/2021 | 50 | 4.2 | 0.3 | 4.2
Cincinnati Children's Hospital | 4/15/2022 | 50 | 4.2 |  | 
National Jewish Health | 10/4/2021 | 250 | 20.8 | 0.0 | 20.8
Nationwide Children's Hospital | 10/4/2021 | Not Provided | Not Provided | 1.5 | 0.0
Peyton Manning Children's Hospital |  | 25 | 2.1 |  | 
U. of California, San Diego | 10/4/2021 | 65 | 5.4 | 0.4 | 5.4
U. of Kentucky Children's Hospital |  | 50 | 4.2 |  | 

## Slide 8: Uptick in Program Exclusion Criteria and Withdrawals to Standard of Care
Home Care’s not having RAD 97’s available (19%) – with the current supply chain delay’s referrals might need to go to other home care’s that do have RAD 97’s in-stock
  Masimo and RHO Leadership working to engage more available home cares for sites
  For active home cares who recently placed an order for RAD 97s it is about 5-7 weeks for delivery

## Slide 9: Implementation Related Problems

## Slide 10
Chart: Recorded Home Oximetry Implementation Trial Related Barriers and Problems
| 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713
Problem Count | 1 | 6 | 2 | 1 | 6 | 4 | 5 | 8 | 5 | 6 | 7 | 13
UCL | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615
+2 Sigma | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 8.5952 | 9.9521
+1 Sigma | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 6.4976 | 7.6427
Average | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333
-1 Sigma | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239
-2 Sigma | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 11: Deviation Types
Last Months
Total Reports | Reports with Deviations | Reports with Deviations (excluding no data captured)
1,138 | 508 | 208

## Slide 12
Goal
Chart: Percent Compliance with the Recorded Home Oximetry Algorithm Across All Implementation Sites
| Jul. 2021 (n=15) | Aug. 2021 (n=51) | Sept. 2021 (n=65) | Oct. 2021 (n=63) | Nov. 2021 (n=75) | Dec. 2021 (n=91) | Jan. 2022 (n=93) | Feb. 2022 (n=121) | Mar. 2022 (n=137) | Apr. 2022 (n=127) | May. 2022 (n=136) | June. 2022 (n=139)
Percent Compliance | 0.66667 | 0.94118 | 0.92308 | 0.9 | 0.91 | 0.96703 | 0.95699 | 0.93388 | 0.87591 | 0.86614 | 0.84559 | 0.7554
UCL | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.96357 | 0.9636 | 0.96357
+2 Sigma | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521 | 0.93521
+1 Sigma | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685 | 0.90685
Average | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849 | 0.87849
-1 Sigma | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013 | 0.85013
-2 Sigma | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177 | 0.82177
LCL | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.79341 | 0.7934 | 0.79341
88%

## Slide 13: Reason’s Why Provider’s Are Not Following the RHO Algorithm’s Recommendation
12% of the time the RHO Algorithm’s Recommendation is not being followed by providers
42% of times the provider has felt comfortable maintaining when the recommendation was to “increase” (5% overall)
What are everyone’s thoughts on improving?
Chart: Reason's For Providers Not Following the RHO Algorithm's Decision
| Growth Concerns | Recent or Current Illness | Feeding Intolerance | Increased WOB | Felt Comfortable Maintaining | Patient Not Seen Outpatient Yet | Data Thought to be Artifact | Other
 | 0 | 0 | 2 | 0 | 38 | 4 | 12 | 41

## Slide 14
Chart: How Physician Compliance with the RHO Algorithm Impacts Duration of HOT
| 90 | 86.666666669999998 | 84.61538462 | 100 | 100 | 91.666666669999998 | 100 | 97.222222220000006 | 100 | 100 | 90.7 | 90 | 100 | 77.8 | 96.6 | 87.5 | 87.5 | 100 | 100 | 100 | 100 | 74.2 | 79.400000000000006 | 100 | 94.4 | 100 | 100 | 94.285714290000001 | 80.952380950000006 | 80 | 90.47619048 | 100
 | 62 | 53 | 38 | 27 | 90 | 127 | 28 | 120 | 25 | 83 | 245 | 28 | 60 | 79 | 97 | 19 | 77 | 22 | 77 | 28 | 23 | 119 | 112 | 64 | 75 | 13 | 9 | 119 | 65 | 42 | 64 | 19
N=32

## Slide 15: HOW MANY INFANTS REQUIRE INCREASES IMMEDIATELY POST DISCHARGE
Number of Infants Eligible to Be Followed By RHO
61
Infants With RHO Data Captured on FIRST download
23 (38%)
Infants who Were Suggested to Increase on the First Download
11 (48%)
*6/10 Increased (60%)
Infants who Were Suggested to Maintained on the First Download
7 (30%)
Infants Who Were Suggested to Wean on the First Download
5 (22%)
*2/5 Infants Actually Weaned
*Download was counted only if 1500 minutes were captured to make recommendation

## Slide 17
(n= 7)
(n= 11)
(n= 3)
(n= 1)

## Slide 18: Family Engagement Survey
  The Family Engagement Pre and Post Implementation Survey Project has been approved by the UMass IRB
  Instructions to submit to local IRBs sent out
  Please reach out to Heather with any questions

## Slide 19: RHO Program Website
All resources, including training documents, the RHO manual, and other templates can be found on the RHO website at www.umassmed.edu/rho-program
Navigate to “Member Login” and log in with the following credentials to access the documents
  Username: RHO
  Password: Oximetry14

## Slide 20: Closing Thoughts
Questions or Comments?
Are there any suggestions and/or feedback on the progress of the program that you would like to share with the team at this time?