## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
September 1, 2022

## Slide 2: Welcome Katie! To the RHO UMMS Team
Katie Edeburn is joining as the new RA at UMMS
Katie will be responsible for RHO downloads, maintaining the REDCap etc. (same activities Crystal and Maria were responsible)
We are thrilled to welcome her!

## Slide 3: RHO Program Implementation Timeline
Feb - Mar 2021
Baseline data collection begins
Mar - May 2021
Initiate site training
Initiate monthly phone calls
May - Aug 2021
Jun 2021 - Feb 2022
Feb - Aug 2022
Aug 2022 - Feb 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
Feb - Aug 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports

## Slide 4
Chart: Site Start Up Progress
| Vanderbilt | Maryland | Kentucky | San Diego | Peyton Manning | Nationwide | Colorado | MGH | New York | Dartmouth | Cincinnati | CHOP | BCH | Arkansas
Executed Contract | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
IRB Approval | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Equipment Available | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
 | - Enrolling
 | - Activated but not enrolling
 | - Patient identified, not yet enrolled

## Slide 5: RHO Implementation Trial Consort Diagram
Average HOT Duration:
70 ± 53

## Slide 6
Goal
Chart: Recorded Home Oximetry Program Implementation Trial Enrollment (July 2021 to Present)
| Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar-22 | Apr-22 | May-22 | Jun-22 | Jul-22 | Aug-22
Participants Enrolled | 3 | 3 | 1 | 5 | 5 | 1 | 8 | 3 | 8 | 3 | 11 | 6 | 11 | 9
UCL | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.5356 | 12.54 | 12.5356 | 12.5356 | 12.5356
+2 Sigma | 10.1904 | 10.1904 | 10.1904 | 10.1904 | 10.1904 | 10.1904 | 10.1904 | 10.1904
+1 Sigma | 7.8452 | 7.8452 | 7.8452 | 7.8452 | 7.8452 | 7.8452 | 7.8452 | 7.8452
Average | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5 | 5.5
-1 Sigma | 3.1548 | 3.1548 | 3.1548 | 3.1548 | 3.1548 | 3.1548 | 3.1548 | 3.1548
-2 Sigma | 0.80958 | 0.80958 | 0.80958 | 0.80958 | 0.80958 | 0.80958 | 0.80958 | 0.80958
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Projected Enrollment | 3.8 | 4.3 | 4.3 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9 | 14.9

## Slide 7: Enrollment by Site
Site Name | 1st patient enrolled | Site IRB Approved | Duration of Implementation in Months | Eligible | Followed | Withdrawn | Active | Weaned | Avg HOT Duration
WAVE 1 |  |  |  |  |  |  |  |  | 
Boston Children's Hospital | 7/8/2021 | 10/4/2021 | 10.9 | 9 | 8 (89%) | 1 | 2 | 5 | 94 ± 90
Dartmouth-Hitchcock | Jan. 2022 | 10/4/2021 | 8.0 | 11 | 11 (100%) |  | 7 | 4 | 42.3 ± 30.2
Maria Fareri Children's | 11/18/2021 | 7/10/2021 | 6.5 | 2 | 2 (100%) |  | 0 | 2 | 90 ± 52
Massachusetts General Hospital | 7/8/2021 | 10/4/2021 | 10.9 | 6 | 5 (83%) | 1 | 2 | 2 | 90.5 ± 40
University of Maryland | 8/21/2021 | 10/4/2021 | 9.5 | 14 | 11 (79%) | 4 | 1 | 6 | 54 ± 39
Vanderbilt | 4/28/2021 | 7/21/2021 | 10.5 | 7 | 2 (29%) |  | 2 | 0 | 
WAVE 2 |  |  |  |  |  |  |  |  | 
Arkansas Children's Hospital | 10/20/2021 | 1/28/2022 | 7.5 | 4 | 4 (100%) | 1 | 2 | 1 | 90
Children's Hospital of Phil. | 5/26/2022 | 10/20/2021 | 7.5 | 13 | 2 (15%) |  | 2 | 0 | 
Cincinnati Children's Hospital |  | 4/15/2022 |  | 0 |  |  | 0 | 0 | 
National Jewish Health |  | 10/4/2021 | 8.0 | 0 |  |  | 0 | 0 | 
Nationwide Children's Hospital | 3/4/2022 | 10/4/2021 | 8.0 | 17 | 13 (76%) | 4 | 9 | 3 | 56 ± 18
Peyton Manning Children's Hospital |  |  |  | 0 |  |  | 0 | 0 | 
U. of California, San Diego | 11/10/2021 | 10/4/2021 | 6.8 | 7 | 3 (43%) | 1 | 2 | 1 | 28
U. of Kentucky Children's Hospital |  |  |  | 0 |  |  | 0 | 0 | 

## Slide 8: Projected vs. Actual Enrollment Into the RHO Program
Site Name | Site IRB Approved | Estimate per Year | Estimate per Month | Current per Month | Estimated enrollment to Date
WAVE 1 |  |  |  |  | 
Boston Children's Hospital | 10/4/2021 | 40 | 3.3 | 0.7 | 13.3
Dartmouth-Hitchcock | 10/4/2021 | 20 | 1.7 | 1.4 | 1.7
Maria Fareri Children's | 7/10/2021 | 14 | 1.2 | 0.3 | 4.7
Massachusetts General Hospital | 10/4/2021 | 13 | 1.1 | 0.5 | 4.3
University of Maryland | 10/4/2021 | 20 | 1.7 | 0.7 | 5.0
Vanderbilt | 7/21/2021 | 70 | 5.8 | 0.2 | 23.3
WAVE 2 |  |  |  |  | 
Arkansas Children's Hospital | 1/28/2022 | 48 | 4.0 | 0.4 | 
Children's Hospital of Phil. | 10/20/2021 | 50 | 4.2 | 0.3 | 4.2
Cincinnati Children's Hospital | 4/15/2022 | 50 | 4.2 |  | 
National Jewish Health | 10/4/2021 | 250 | 20.8 | 0.0 | 20.8
Nationwide Children's Hospital | 10/4/2021 | Not Provided | Not Provided | 1.5 | 0.0
Peyton Manning Children's Hospital |  | 25 | 2.1 |  | 
U. of California, San Diego | 10/4/2021 | 65 | 5.4 | 0.4 | 5.4
U. of Kentucky Children's Hospital |  | 50 | 4.2 |  | 

## Slide 9: Update on Action Item’s from Our Last Meeting
Poor Signal Quality: Received new report information from Masimo to include low signal quality. UMMS and Dartmouth teams working on analyzing a sub-set of patients to determine impact of low signal quality.
Supply Chain Shortage: Masimo production of RAD 97’s is ramping back up. Most home cares with outstanding orders should receive in the next several weeks.

## Slide 10: Family Engagement Survey
  The Family Engagement Pre and Post Implementation Survey Project has been approved by the UMass IRB
  Instructions to submit to local IRBs sent out on 6/7
  Please reach out to Heather with any questions

## Slide 11: New Centralized Email
Please now send all enrollment updates to RHOProgram@umassmed.edu
All UMMS RHO members have access and can address questions/queries in a timely manner

## Slide 12: Cost of Implementing the RHO Program
PCORI is interested in understanding the cost of implementing successful programs as standard of care
If awarded, we would be asking sites to complete a short survey with help from their CFO (or appropriate staff) on the cost of implementation at their site
Additionally, site’s will be queried at two-random times to collect data on the time spent carrying out RHO related tasks (bi-weekly phone calls, documentation, or telehealth visits)

## Slide 13
Chart: Implementation: Average Duration of Home Oxygen Therapy for Infants Followed by the RHO Program Across All Implementation Sites
| Q2 2021 (n=2) | Q3 2021 (n=5) | Q4 2021 (n=8) | Q1 2022 (n=10) | Q2 2022 (n=9)
Avg HOT Duration | 102 | 121.4 | 73.75 | 75.4 | 44.2222
UCL | 162.888 | 162.888 | 162.888 | 162.888 | 162.888
+2 Sigma | 136.3768 | 136.3768 | 136.3768 | 136.3768 | 136.3768
+1 Sigma | 109.8656 | 109.8656 | 109.8656 | 109.8656 | 109.8656
Average | 83.3544 | 83.3544 | 83.3544 | 83.3544 | 83.3544
-1 Sigma | 56.8433 | 56.8433 | 56.8433 | 56.8433 | 56.8433
-2 Sigma | 30.3321 | 30.3321 | 30.3321 | 30.3321 | 30.3321
LCL | 3.8209 | 3.8209 | 3.8209 | 3.8209 | 3.8209

## Slide 14
Chart: Control: Average Duration of Home Oxygen Therapy for Infants Not Followed by the RHO Program Across All Implementation Sites
| Q3 2021 (n=1) | Q1 2022 (n=2) | Q2 2022 (n=2)
Average HOT Duration | 184 | 46.5 | 45
UCL | 276.7033 | 276.7033 | 276.7033
+2 Sigma | 215.08 | 215.08 | 215.08
+1 Sigma | 153.4567 | 153.4567 | 153.4567
Average | 91.8333 | 91.8333 | 91.8333
-1 Sigma | 30.21 | 30.21 | 30.21
-2 Sigma | -31.4133 | -31.4133 | -31.4133
LCL | -93.0367 | -93.0367 | -93.0367

## Slide 15: Implementation Related Problems

## Slide 16
Chart: Recorded Home Oximetry Implementation Trial Related Barriers and Problems
| 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774
Problem Count | 1 | 6 | 2 | 1 | 6 | 4 | 5 | 8 | 5 | 6 | 7 | 13 | 3 | 4
UCL | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615 | 12.2615
+2 Sigma | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 9.9521 | 8.5952 | 9.9521 | 9.9521 | 9.9521
+1 Sigma | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 7.6427 | 6.4976 | 7.6427 | 7.6427 | 7.6427
Average | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333 | 5.3333
-1 Sigma | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239 | 3.0239
-2 Sigma | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453 | 0.71453
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 17: Deviation Types
Last Months
Total Reports | Reports with Deviations | Reports with Deviations (excluding no data captured)
1,742 | 633 | 294

## Slide 18
Goal
88%
Chart: Percent Compliance with the Recorded Home Oximetry Algorithm Across All Implementation Sites
| Jul. 2021 (n=15) | Aug. 2021 (n=51) | Sept. 2021 (n=65) | Oct. 2021 (n=63) | Nov. 2021 (n=75) | Dec. 2021 (n=91) | Jan. 2022 (n=93) | Feb. 2022 (n=121) | Mar. 2022 (n=137) | Apr. 2022 (n=127) | May. 2022 (n=136) | June. 2022 (n=139) | July. 2022 (n=154) | August. 2022 (n=188)
Percent Compliance | 0.66667 | 0.94118 | 0.92308 | 0.9 | 0.91 | 0.96703 | 0.95699 | 0.93388 | 0.87591 | 0.86614 | 0.84559 | 0.7554 | 0.83117 | 0.84043
UCL | 0.96806 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.97052 | 0.9636 | 0.97052 | 0.97052 | 0.9705
+2 Sigma | 0.93617 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.93863 | 0.97388
+1 Sigma | 0.90428 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.90674 | 0.92436
Average | 0.87239 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485 | 0.87485
-1 Sigma | 0.8405 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.84296 | 0.82533
-2 Sigma | 0.80861 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.81107 | 0.77582
LCL | 0.77672 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.77918 | 0.78

## Slide 19: Compliance Rate’s and Individual Infant’s Duration of HOT
Chart: How Physician Compliance with the RHO Algorithm Impacts Duration of HOT
| 90 | 86.666666669999998 | 84.61538462 | 100 | 100 | 91.666666669999998 | 100 | 97.222222220000006 | 100 | 100 | 90.7 | 90 | 93.333333333333329 | 100 | 83.333333333333343 | 100 | 100 | 94.285714290000001 | 80.952380950000006 | 80 | 90.47619048 | 100 | 87.5 | 87.5 | 54.545454545454547 | 66.666666666666671 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 75.675675675675677 | 79.411764705882348 | 94.444444444444443 | 100 | 87.5 | 94.444444444444443
 | 62 | 53 | 38 | 27 | 90 | 127 | 28 | 120 | 25 | 83 | 245 | 28 | 152 | 60 | 96 | 13 | 9 | 119 | 65 | 42 | 64 | 19 | 19 | 77 | 40 | 60 | 22 | 77 | 28 | 23 | 77 | 33 | 7 | 17 | 119 | 112 | 75 | 36 | 38 | 186

## Slide 20
Chart: Site Compliance Rate and Impact on Average HOT Duration
| E | N | F | K | A | B
Average HOT Duration (days) | 112.3333 | 112 | 105.5 | 50.4286 | 46 | 35.5
Compliance (%) | 0.89241 | 0.74011 | 0.88087 | 0.944 | 0.7971 | 0.98805

## Slide 21: How does Initial Flow Rate Impact Duration?
Chart: UNADJUSTED: Sites' Average Starting O2 Flow Rate Compared to Average HOT Duration
| E | N | F | K | A | B
Average HOT Duration (days) | 112.3333 | 112 | 105.5 | 50.4286 | 46 | 35.5
Average Starting O2 (cc/min) | 357 | 310 | 200 | 446 | 625 | 168
Chart: ADJUSTED: Sites' Average Starting O2 Flow Rate Compared to Average HOT Duration (corrected)
| E | N | F | K | A | B
Average HOT Duration (days) | 112.3333 | 112 | 105.5 | 50.4286 | 46 | 35.5
Average Starting O2 (cc/min) | 500 | 250 | 250 | 500 | 500 | 125

## Slide 22: RHO to be Presented as a Poster at the Annual VON Conference

## Slide 23: RHO Program Website
All resources, including training documents, the RHO manual, and other templates can be found on the RHO website at www.umassmed.edu/rho-program
Navigate to “Member Login” and log in with the following credentials to access the documents
  Username: RHO
  Password: Oximetry14

## Slide 24: Closing Thoughts
Questions or Comments?
Are there any suggestions and/or feedback on the progress of the program that you would like to share with the team at this time?