September 1st, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Katie Edeburn, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- All sites have been activated!

- 12 out of 14 sites are actively recruiting

Enrollment

- A total of 74 babies followed have been followed to date, 41 have weaned with an average HOT duration of 70 days ± 53

- Enrollment estimates predicted about 15 babies being enrolled per month, currently the average enrollment per month is 5.5 babies

Update on Action Items from Last Month’s Meeting

- Tyler (Dartmouth) and Heather are working on analyzing a sub-set of infant’s data correcting for low signal quality – data will be presented at next month’s meeting

- Supply chain shortage: Masimo production of the RAD 97’s is ramping back up. Home cares with pending orders should receive shipments in the next few weeks

Family Satisfaction Survey

- The project has been approved as non-human subject research by UMMS IRB

- Please submit to your local IRB’s and contact Heather with any questions

New Centralized Email

- Please send all new enrollments to RHOProgram@umassmed.edu

- Additionally, all inquiries and questions can be sent to this central email as both Katie and

Heather both monitor throughout the day

Cost of Implementation

- PCORI is interested in understanding the cost associated with implementation of successful programs, like the RHO Program

- If awarded funding, we will be asking site PI’s to work with the administration to complete a short survey and participate in a focus group

- Additionally, sites will be queried at 2-random time points to collect data on the time spent on RHO related activities (reviewing data, patient phone calls, telehealth appointments etc.)

Other Questions and Discussed Topics

- Dr. Ryu asked about making data available to families. Heather to investigate use of the Masimo SafetyNET application in which families can access data

- Point raised about looking at duration of oxygen corrected for birth gestational age and corrected gestational age – still not enough babies weaned to complete analysis but plan to correct for different baseline factors

- Dr. Hartman raised the question on if infants with PPHN receive a negative ECHO do they return to the normal RHO protocol or stay on the modified PPHN protocol – Dr. Austin weighed in that he would require two negative ECHO’s before returning them to the standard protocol and would actually keep them on the modified protocol with the intention to treat

- More home care companies are stocking RAD 97’s which may make them more available or be utilized more commonly by patients that don’t qualify for the enrollment in the RHO program

- Dr. Ryu mentioned that now in their area there are now supply issues with probes – Heather to investigate further with what type of probe and when more stock becomes available

Next Investigator Meeting will be on October 13th  at 4pm EST