July 7th, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Arkansas Children’s Hospital |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| U. of Kentucky Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
|  |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- All but one site has been activated

- 11 out of 14 sites are actively recruiting

Enrollment

- A total of 61 babies followed have been followed to date, 22 have weaned with an average HOT duration of 74 days

- Primary reason for exclusion from program is a RAD 97 being unavailable

  - Working with Masimo to supply more homecare companies with RAD 97’s

  - Please try to refer eligible babies to home care companies in your area that currently have RAD 97’s available

  - Currently some of our more active home care companies do not have RAD 97’s available as they are waiting on equipment shipments. Masimo is reporting a 5–7-week delay in shipping. In the meantime, referrals may have to be placed with home cares in your area with equipment on their shelves.

- Enrollment estimates predicted about 15 babies being enrolled per month, currently the average enrollment per month is 4.6 babies

Projected vs Actual N of Infants Being Followed

- There has been a dip in enrollment across sites

- Discussion around potential factors contributing to low enrollment numbers and this may be due to higher estimates in grant planning

Family Satisfaction Survey

- The project has been approved as non-human subject research by UMMS IRB

- Please submit to your local IRB’s and contact Heather with any questions

Increase in Non-Compliance and Reason of “Providers Not Following the RHO Algorithm”

- Providers are noticing an increase in the time spent below each target saturation for older more active patients, in these cases they are not following when the time below 93% suggests an increase.

  - Active discussion around older babies becoming more mobile and active (kicking around) at 2-3 months corrected gestational age. Consensus decision to change the protocol slightly to recommend at 3 months corrected gestational age to only monitor (use oximeter) nocturnally.

  - Heather will be updating the program manual to reflect this change and PDSA cycle

- We are working with Masimo on obtaining the algorithm parameters used by the RAD 97 to determine artifact to determine if the python analyzing program needs to be updated.

  - Dr. Demauro suggested eliminating all “0” oxygen saturations

  - Will update everyone of any changes made to the algorithm’s analysis program

High Percentage of First Downloads Requiring an Increase

- Active discussion around the need for increasing the initial discharge flow rate at the time of the first download and potential reasons for this. A total of 48% of babies have required an increase in flow to date. Two theories are that (a) more intermittent hypoxia is occurring prior to discharge or (b) different equipment and delivery of supplemental oxygen compared to NICU is under supporting the infant

- Dr. Hysinger noted at their institution they monitored infants pre-discharge and found that roughly 45% of infants had significant hypoxemia prior to discharge, consistent with our finding.

- Dr. Shepherd mentioned that their practice is to obtain a nocturnal recording a week before discharge to evaluate for hypoxemia on current flow rate. If the baby is unable to meet criteria, they are bumped to the next level and the test is repeated.

Next Investigator Meeting will be on August 4th at 4pm EST