## Slide 1: The Recorded Home Oximetry (RHO) Program Monthly Investigator Meeting
November 3, 2022

## Slide 2: RHO Program Implementation Timeline
Feb - Mar 2021
Baseline data collection begins
Mar - May 2021
Initiate site training
Initiate monthly phone calls
May - Aug 2021
Jun 2021 - Feb 2022
Feb - Aug 2022
Aug 2022 - Feb 2023
Complete site training
Reach 33% of eligible families
Reach 66% of eligible families
Feb - Aug 2023
Reach 100% of eligible families
Initiate 18-month implementation
Begin providing monthly feedback reports
Notes: - Unchecked the goal to reach 66% as we have not fulfilled throughout the milestone period but are on our way

## Slide 3
Chart: Site Start Up Progress
| Vanderbilt | Maryland | Kentucky | San Diego | Peyton Manning | Nationwide | Colorado | MGH | New York | Dartmouth | Cincinnati | CHOP | BCH | Arkansas
Executed Contract | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33 | 0.33
IRB Approval | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
Equipment Available | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333 | 0.33333
 | - Enrolling
 | - Activated but not enrolling
 | - Patient identified, not yet enrolled

## Slide 4: RHO Implementation Trial Consort Diagram
Average HOT Duration:
72 ± 23

## Slide 5
Goal
Chart: Recorded Home Oximetry Implementation Trial Enrollment (Q3 2021 to Present)
| Q3 2021 | Q4 2021 | Q1 2022 | Q2 2022 | Q3 2022 | Q4 2022
Total | 7 | 11 | 20 | 24 | 44 | 15
UCL | 42.112 | 57.912 | 57.912 | 57.912 | 57.912 | 57.912
+2 Sigma | 30.408 | 46.208 | 46.208 | 46.208 | 46.208 | 46.208
+1 Sigma | 18.704 | 34.504 | 34.504 | 34.504 | 34.504 | 34.504
Average | 7 | 22.8 | 22.8 | 22.8 | 22.8 | 22.8
-1 Sigma | -4.704 | 11.096 | 11.096 | 11.096 | 11.096 | 11.096
-2 Sigma | -16.408 | -0.608 | -0.608 | -0.608 | -0.608 | -0.608
LCL | -28.112 | -12.312 | -12.312 | -12.312 | -12.312 | -12.312
Target Enrollment | 12 | 23 | 45 | 63 | 88 | 88

## Slide 6: Enrollment by Site
Site Name | 1st Patient Enrolled | Duration of Implementation | Estimate Per Year | Estimate Per Month | Current Per Month | Followed | Withdrawn | Weaned from HOT | Active on HOT | Average | SD
Boston Children's | 7/8/2021 | 15.37 | 40 | 3 | 0.7 | 12 | 1 | 8 | 3 | 101.63 | 72.76
Dartmouth-Hitchcock | 1/1/2022 | 9.47 | 20 | 2 | 1.8 | 18 | 1 | 12 | 5 | 71.25 | 73.72
Maria Fareri Children's Hospital | 11/18/2021 | 10.93 | 14 | 1 | 0.2 | 2 | 0 | 2 | 0 | 90.00 | 37.00
Massachusetts General Hospital | 7/8/2021 | 15.37 | 13 | 1 | 0.4 | 6 | 1 | 4 | 1 | 112.00 | 59.33
University of Maryland | 8/21/2021 | 13.90 | 20 | 2 | 1.2 | 17 | 6 | 9 | 2 | 57.67 | 37.75
Vanderbilt | 4/28/2021 | 17.73 | 70 | 6 | 0.1 | 2 | 2 | 0 | 0 |  | 
Arkansas Children's Hospital | 10/20/2021 | 11.90 | 48 | 4 | 1.0 | 13 | 5 | 4 | 4 | 98.00 | 59.55
Children's Hospital of Philidelphia | 5/26/2021 | 16.80 | 50 | 4 | 0.2 | 3 | 1 | 2 | 0 | 51.00 | 27.36
Cincinnati Children's Hopsital | 9/21/2022 | 0.70 | 50 | 4 | 0.7 | 1 | 0 | 0 | 1 |  | 
National Jewish Health | 8/24/2022 | 1.63 | 250 | 21 | 3.8 | 9 | 0 | 0 | 9 |  | 
Nationwide Children's Hospital | 3/4/2022 | 7.40 | 75 | 6 | 3.2 | 26 | 8 | 9 | 9 | 46.33 | 38.86
Payton Manning Children's Hospital | 7/19/2022 | 2.83 | 25 | 2 | 1.7 | 6 | 3 | 2 | 1 | 11.00 | 6.24
U. of California, San Diego | 11/10/2021 | 11.20 | 65 | 5 | 0.5 | 6 | 2 | 3 | 1 | 91.67 | 78.45
U. of Kentucky Children's Hospital |  | 1494.87 | 50 | 4 | 0.0 | 0 | 0 | 0 | 0 |  | 
Total |  |  |  |  |  | 121 | 25 | 55 | 36 | 73.05 | 23.78

## Slide 7: Implementation Trial Outcomes

## Slide 8
Chart: Implementation: Average Duration of Home Oxygen Therapy for Infants Followed by the RHO Program Across All Implementation Sites
| Q2 2021 (n=2) | Q3 2021 (n=5) | Q4 2021 (n=9) | Q1 2022 (n=12) | Q2 2022 (n=13) | Q3 2022 (n=14) | Q4 2022 (n=1)
Avg HOT Duration | 102 | 121.4 | 83.6364 | 101 | 71.3077 | 37.1429 | 17
UCL | 179.3658 | 179.3658 | 179.3658 | 179.3658 | 179.3658 | 179.3658 | 179.3658
+2 Sigma | 153.2439 | 153.2439 | 153.2439 | 153.2439 | 153.2439 | 153.2439 | 153.2439
+1 Sigma | 127.1219 | 127.1219 | 127.1219 | 127.1219 | 127.1219 | 127.1219 | 127.1219
Average | 101 | 101 | 101 | 101 | 101 | 101 | 101
-1 Sigma | 74.8781 | 74.8781 | 74.8781 | 74.8781 | 74.8781 | 74.8781 | 74.8781
-2 Sigma | 48.7561 | 48.7561 | 48.7561 | 48.7561 | 48.7561 | 48.7561 | 48.7561
LCL | 22.6342 | 22.6342 | 22.6342 | 22.6342 | 22.6342 | 22.6342 | 22.6342

## Slide 9
Chart: Control: Average Duration of Home Oxygen Therapy for Infants Not Followed by the RHO Program Across All Implementation Sites
| Q3 2021 (n=1) | Q1 2022 (n=2) | Q2 2022 (n=9) | Q3 2022 (n=1)
Average HOT Duration | 184 | 46.5 | 94.3333 | 101
UCL | 276.6983 | 276.6983 | 276.6983 | 276.6983
+2 Sigma | 219.9517 | 219.9517 | 219.9517
+1 Sigma | 163.205 | 163.205 | 163.205
Average | 106.4583 | 106.4583 | 106.4583 | 106.4583
-1 Sigma | 49.7117 | 49.7117 | 49.7117
-2 Sigma | -7.035 | -7.035 | -7.035
LCL | -63.7817 | -63.7817 | -63.7817

## Slide 10: Duration By Starting Flow Rate

## Slide 11: Duration by Highest Flow Rate Reached

## Slide 12: Implementation Related Problems

## Slide 13
Chart: Recorded Home Oximetry Implementation Trial Related Barriers and Problems
| 44378 | 44409 | 44440 | 44470 | 44501 | 44531 | 44562 | 44593 | 44621 | 44652 | 44682 | 44713 | 44743 | 44774 | 44805 | 44835
Problem Count | 1 | 6 | 2 | 1 | 6 | 4 | 5 | 8 | 5 | 6 | 9 | 13 | 3 | 5 | 6 | 13
UCL | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452 | 13.0452
+2 Sigma | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 10.6343 | 8.5952 | 10.6343 | 10.6343 | 10.6343 | 10.6343
+1 Sigma | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 8.2234 | 6.4976 | 8.2234 | 8.2234 | 8.2234 | 8.2234
Average | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125 | 5.8125
-1 Sigma | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016 | 3.4016
-2 Sigma | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067 | 0.99067
LCL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Slide 14: Deviation Types
Total Reports | Reports with Deviations | Reports with Deviations (excluding no data captured)
2,230 | 693 | 377
Last Months

## Slide 15
Goal
Chart: Percent Compliance with the Recorded Home Oximetry Algorithm Across All Implementation Sites
| Jul. 2021 (n=15) | Aug. 2021 (n=51) | Sep. 2021 (n=65) | Oct. 2021 (n=63) | Nov. 2021 (n=75) | Dec. 2021 (n=91) | Jan. 2022 (n=93) | Feb. 2022 (n=122) | Mar. 2022 (n=154) | Apr. 2022 (n=149) | May. 2022 (n=164) | Jun. 2022 (n=174) | Jul. 2022 (n=155) | Aug. 2022 (n=205) | Sep. 2022 (n=207) | Oct. 2022 (n=189)
Percent Compliance | 0.66667 | 0.94118 | 0.92308 | 0.9 | 0.91 | 0.96703 | 0.95699 | 0.93443 | 0.88961 | 0.86577 | 0.86585 | 0.8046 | 0.82581 | 0.84878 | 0.86473 | 0.8836
UCL | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872 | 0.98872
+2 Sigma | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182 | 0.95182
+1 Sigma | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491 | 0.91491
Average | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801 | 0.87801
-1 Sigma | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411 | 0.8411
-2 Sigma | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042 | 0.8042
LCL | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673 | 0.7673
Goal | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9

## Slide 16: Updates

## Slide 17: PCORI Funding
Heather Working on Budget
Stay Tuned!

## Slide 18: Low-Quality Signal Exclusion
New Algorithm Started Last Week
Automatically Removes Signal Marked as “Low-Quality”
Still Perfecting the Process

## Slide 19: Importance of Changing Probes
Put in an image of data that is affected by probe
Have at least three separate babies who were seeing data like this and then switched probes and everything was fine

## Slide 20: Discussion Points

## Slide 21: Reminders

## Slide 22: Data Queries
Early December
Missing Values and Forms in REDCap

## Slide 23: Upper Respiratory Infections
RSV Season
If Serious Enough for Hospital Visit
  Please fill out REDCap AE form
If Not Serious Enough for Hospital Visit
  Please still inform us in download response emails
  We are looking to record this data incase it has a future impact

## Slide 24: No Heather
Heather in on vacation through December
Please email Katie if you need anything
Emails to Heather will not be answered swiftly

## Slide 25: Family Engagement Survey
For Sites w/out IRB Approval:
Instructions to submit to local IRBs sent out on 6/7
Please reach out to Heather and Katie with any questions/concerns/barriers
For Sites w/ IRB Approval:
Please Send Survey Links At Initial Discharge and After HOT Weaning
Spanish Version Coming very soon!

## Slide 26: RHO Program Website
All resources, including training documents, the RHO manual, and other templates can be found on the RHO website at www.umassmed.edu/rho-program
Navigate to “Member Login” and log in with the following credentials to access the documents
  Username: RHO
  Password: Oximetry14

## Slide 27: Closing Thoughts
Questions or Comments?
Are there any suggestions and/or feedback on the progress of the program that you would like to share with the team at this time?