# March 7th, 2024

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Katie Edeburn, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Tyler Allcroft, Research Coordinator |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Enrollment

- A total of 339 babies have been followed to date, 192 have weaned with an average HOT duration of 76 days ± 62 days.

- Enrollment estimates predicted about 66 infants being enrolled per month, enrollment for the past month was 3.

New Variables

- There are new forms live in the REDCap related to growth, pulmonary medications, COI, and a few other additional variables. Instructions for each can be found in the information section at the top of each form.

  - For the growth forms the measurements can come from any visit in your EMR that is within the requested time period, it does not have to be only measurements from your pulmonary clinic.

- These new variables will not be mandatory to include at this time but will be for all subjects eligible for RHO, including those who have already weaned using RHO.

- Any questions can be directed to Katie or Heather.

Upcoming Surveys

- Pending IRB approval, a survey about the cost of RHO will be sent out soon to those involved in the budgeting of each site. This quantitative survey should be released by the end of March and should be filled out by someone at your site knowledgeable about your budget. It will involve questions about volume, start-up costs, and operating costs as your site.

- Focus groups open to anyone participating in RHO will also be launching soon.

- We hope the data here help us determine the best model to continue with RHO after the conclusion of this trial.

Miscellaneous Reminders

- New sub-awards will be distributed in the coming weeks, continuing through our enrollment end-date on July 31st, 2024.

  - All children enrolled on or before this date will be followed until they wean.

- All sites should be sending out pre/post family assessment surveys to families involved in RHO. If you are unsure about how this project stands at your site, please reach out to Katie and Heather.

- All control subjects should have screening and demographics forms filled out in REDCap, so we are aware of their existence while we wait for them to wean.

- When the recommendation is to maintain, patients can be contacted through the EMR instead of phone calls at the discretion of your site.

- If you have any difficulties with REDCap or general questions, please reach out to Katie (Katherine.Edeburn@umassmed.edu)

- Heather has returned full-time to PA School. If your question requires prompt attention, please email Katie or the RHO Program central email (RHOprogram@umassmed.edu)

Next Investigator Meeting will be on April 4th at 4pm EST