October 13th, 2022

4:00-5:00 PM EST

RHO Implementation Monthly Investigator Call Minutes

| Invitees/Attendees: |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Dr. Larry Rhein, Principal Investigator |  | Boston Children’s Hospital |  | Maria Fareri Children’s Hospital |  |
| Heather White, Project Coordinator |  | Children’s Hospital of Philadelphia |  | Massachusetts General Hospital |  |
| Lindsey Simoncini, Research Coordinator |  | Cincinnati Children’s Hospital |  | Nationwide Children’s Hospital |  |
| Katie Edeburn, Research Assistant |  | National Jewish Health, Colorado |  | Peyton Manning Children’s Hospital |  |
| Arkansas Children’s Hospital |  | Dartmouth-Hitchcock Medical Center |  | U. of California, San Diego |  |
| U. of Kentucky Children’s Hospital |  | University of Maryland |  | Vanderbilt |  |

Startup/progress

- All sites have been activated!

- 14 out of 14 sites are actively recruiting

Enrollment

- A total of 101 babies followed have been followed to date, 41 have weaned with an average HOT duration of 69 days ± 53

- Enrollment estimates predicted about 16 babies being enrolled per month, currently the average enrollment per month is 6.5 babies

New Centralized Email

- Please send all new enrollments as well as inquiries and questions to RHOProgram@umassmed.edu , Katie and Heather monitor it throughout the day

Update on Enrollments and Withdrawals

- Withdrawal rate currently stands at about 24%, this rate is higher than expected. Active discussion on ways to reduce

  - Most common reason has been issues with equipment. Now that supply chain is up to normal production, we should see the number of infants being withdrawn due to no replacement monitors go down.

- When parents self-wean that is not an automatic withdrawal, they may remain enrolled in the program, and we can still use their data, considering this deviation

- Parent frustration with non-functioning devices and discrepancies between algorithm recommendations and perceived health of baby is major cause in withdrawal and something we are working actively to address

Update on Low-Quality Signal Concerns

- In final stages of designing and implementing new function within our algorithm that automatically removes data points of low signal quality (instances when the waveform on the RAD 97 is low)

- UMASS and Dartmouth are collaborating to retrospectively look at previous data and analyze how much of the data would be considered artifact and possible variables influencing the quality

- Variables to be collected and analyzed for their impact on low signal quality are: (1) age; (2) race/ethnicity; (3) day vs. nighttime data; (4) flow rate

Cost of Implementation

- PCORI is interested in understanding the cost associated with implementation of successful programs, like the RHO Program

- If awarded funding, we will be asking site PI’s to work with their administration to complete a short survey and participate in a focus group

- Additionally, sites will be queried at 2-random time points to collect data on the time spent on RHO related activities (reviewing data, patient phone calls, telehealth appointments etc.)

- Awaiting final approval and funding announcement

Family Engagement Survey

- The project has been approved as non-human subject research by UMMS IRB

- Only 3 of 15 sites have approved IRBs

- Please submit to your local IRB’s and contact Heather with any questions

SDoH and HOT Duration Spin-Off Project

- Goal is to identify factors of social determinants of health (SDoH) that may impact HOT duration

- Assesses if there is a relationship between childhood opportunity index (COI), insurance type, housing type, race, ethnicity, and possible other environmental and demographic factors

- It would involve a separate IRB submission for address extraction – secondary use of retrospective data, waiver of content (covered under current DUA)

- If you are interested in participating in this data collection (zip code abstraction) please contact Heather and John Levin (Jonathan.Levin@childrens.harvard.edu) or Kristen Richard at (Kristen.Richard@childrens.harvard.edu)

Other Questions and Discussed Topics

- Thank you again for participating in our study and have a wonderful month :)

Next Investigator Meeting will be on November 3rd at 4pm EST